## Project Planner
Victoria State Accident DataSet
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create GitHub Repository | 1 | 1 | 1 | 1 | 100%
Clone Github Repository | 2 | 2 | 2 | 2 | 100%
Create Google Documents | 2 | 2 | 2 | 2 | 100%
Constant Git Updates | 3 | 60 | 3 | 57 | 0%
Pick the Dataset | 4 | 2 | 4 | 2 | 100%
Discuss the work split | 5 | 2 | 5 | 1 | 100%
1.0 of Project Plan | 6 | 1 | 6 | 1 | 100%
Work Breakdown Structure | 10 | 3 | 10 | 3 | 100%
Activity definition | 10 | 3 | 12 | 3 | 100%
Gantt Chart | 13 | 3 | 14 | 2 | 100%
Project Background | 6 | 1 | 6 | 1 | 100%
System Overview | 7 | 1 | 7 | 1 | 100%
Potential Benefits | 8 | 1 | 8 | 1 | 100%
User Requirements | 10 | 1 | 10 | 1 | 100%
Software Requirements | 12 | 1 | 12 | 1 | 100%
Use Cases and Diagrams | 13 | 3 | 13 | 4 | 100%
Software Design Flowchart | 13 | 3 | 14 | 4 | 100%
System Components | 16 | 4 | 20 | 3 | 100%
User Interface Design | 20 | 3 | 23 | 3 | 100%
Structural Design | 23 | 3 | 26 | 3 | 100%
Visual Design | 26 | 3 | 29 | 3 | 100%
Create Python Files | 33 | 1 | 30 | 1 | 100%
Code the Software | 35 | 21 | 33 | 27 | 85%
Create User Manual | 53 | 2 | 59 | 1 | 100%
12-Month Summary | 53 | 4 | 59 | 1 | 100%
Log all Git Updates | 33 | 21 | 33 | 27 | 100%
Make a Testing Plan | 33 | 2 | 35 | 1 | 100%
Perform Testing | 35 | 21 | 36 | 27 | 100%
Fix Bugs | 35 | 21 | 36 | 27 | 100%
Final Debugging | 53 | 60 | 50 | 10 | 100%
Testing Report | 35 | 21 | 58 | 2 | 100%